## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2235-swen-261-03-i BCNS
Testing Team Name | BCNS

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
AS a Helper I WANT to add needs to my funding basket SO THAT I can buy multiple needs at once | GIVEN that I am interested in a need WHEN I add it to my funding basket, THEN I expect the need to be in my funding basket for future purchase and should return a status code of 200 (OK). | Pass | ST 3/03
| GIVEN that I am interested in a need WHEN I add it to my funding basket and it no longer exists, THEN I expect the need to not be in my funding basket and should return a status code of 409 (NOT FOUND). | Pass | ST 3/03
AS a Helper I WANT to delete needs from my funding basket SO THAT I can easily manage and refine my selection, ensuring my contributions align with my current preferences and priorities. | GIVEN that I am no longer interested in a need WHEN I remove it from my funding basket, THEN I expect the need to no longer be there and should return a status code of 200 (OK). | Pass | ST 3/03
| GIVEN that I am no longer interested in a need WHEN I remove it from my funding basket and it already does not exist, THEN I expect the need to no longer be there and should return a status code of 208 (ALREADY REPORTED). | Pass | ST 3/03
AS a Helper I WANT to buy the needs SO THAT I can efficiently assist and address the unique challenges faced by the non-profit organization. | GIVEN that I am ready to buy my need(s) WHEN I checkout the needs from the funding basket, THEN I expect to see details pertaining to my purchase (such as quantity of items and delivery time) and should return a status code of 200 (OK). | Pass | CM 3/18
| GIVEN that I have checked out my needs, THEN I expect my Funding Basket to be empty and the needs checked out to be visible in my Purchase History and should return a status code of 200 (OK). | Pass | BG 3/18
AS a Helper I WANT TO be able to logout with the contents of my funding basket saved SO THAT I can manage my support efficiently without the fear of losing progress. | GIVEN that I am interested in a need and want to consider buying it later WHEN I save the need to my Funding Basket, THEN I expect the need to be in my funding basket when I login next time and should return a status code of 200 (OK). | Pass | CM 3/18
| GIVEN that I am interested in a need and want to consider buying it later WHEN I save the need to my Funding Basket and it no longer exists, THEN I expect the need to no longer be in my funding basket and should return a status code of 410 (GONE). | Pass | CM 3/18
AS A Helper I WANT TO view the items in my Funding Basket SO THAT I can decide what items to fund. | GIVEN I select the "Funding Basket" page of the site WHEN I am authenticated as a Helper, THEN I expect to see a list of the items in my Funding Basket. | Pass | NH 3/19
| GIVEN I access the Funding Basket page WHEN there are no items in my Funding Basket, THEN I expect to see a message indicating that my funding basket is empty. | Pass | NH 3/19
AS a Manager I WANT to add a need to the Needs Cupboard SO THAT it will be available for Helpers to select. | GIVEN that I want to present a new need to the customer WHEN I add a need to the Cupboard, THEN I expect the need to be available for customers to purchase and should return a status code of 200 (OK). | Pass | BG 2/28
| GIVEN that I want to present a new need to the customer WHEN I add a need to the Cupboard and it already exists, THEN I expect the need to already be available for customers to purchase and should return a status code of 208 (ALREADY MENTIONED). | Pass | BG 2/28
AS a Manager I WANT to remove a need from the Needs Cupboard SO THAT it will no longer be available for Helpers to select. | GIVEN that I am no longer presenting a need to a customer WHEN I delete a need from the Cupboard, THEN I expect the need to no longer appear on the Cupboard and should return a status code of 200 (OK). | Pass | CM 2/28
| GIVEN that I am no longer presenting a need to a customer WHEN I delete a need from the Cupboard and it already has been deleted, THEN I expect the system to return a status code of 201 (CONFLICT). | Pass | CM 2/28
As a Manager I WANT to login securely with my credentials SO THAT I can manage the cupboards. | GIVEN that I enter my credentials WHEN I wish to access my account, THEN I expect to be logged in to my account to manage needs from the cupboard and should return a status code of 200 (OK). | Pass | NH 3/16
| GIVEN that I enter my credentials WHEN I wish to access my account and I enter them incorrectly, THEN I expect to see an error message saying I entered incorrect credentials and should return a status code of 404 (NOT FOUND). | Pass | NH 3/16
AS a Helper I WANT to login securely with my credentials SO THAT I can purchase needs from the cupboard. | GIVEN that I enter my credentials WHEN I wish to access my account, THEN I expect to be logged in to my account to purchase needs from the cupboard and should return a status code of 200 (OK). | Pass | NH 3/16
| GIVEN that I enter my credentials WHEN I wish to access my account and I enter them incorrectly, THEN I expect to see an error message saying I entered incorrect credentials and should return a status code of 404 (NOT FOUND). | Pass | NH 3/16
AS a Helper I WANT to see a list of needs SO THAT I can choose which ones to contribute to. | GIVEN that I am looking for needs WHEN I browse needs from the Cupboard, THEN I expect to see details pertaining to needs being offered and should return a status code of 200 (OK). | Pass | ST 2/28
| GIVEN that I am looking for needs WHEN I browse needs from the Cupboard and there are no needs to browse, THEN I expect to see no needs on the Cupboard and should return a status code of 204 (NO CONTENT). | Pass | BG 2/28
| GIVEN that I am interested in a need WHEN I check the need's availability and there is none left, THEN I expect to see an out of stock message and should return a status code of 410 (GONE). | Pass | BG 2/28
As a Helper I want to search for a Need so that I can locate what I want to purchase. | WHEN I enter a keyword into the search bar WHEN I am on the Needs page, THEN I expect to see a list of needs matching that keyword. | Pass | BG 2/28